## MAIN (hidden)
2023-09-13
2021 JPR - Dougherty Conference Center, Offut AFB, NE (October 19-21)
| Main Deliverable | Action Items | Who's Responsible? | Notified? | Due Date | Complete? | Notes/Last Touch
| First Contact: | Dates Final? | Darnell | Yes | 2021-07-12 | Yes
|  | Location Final | Darnell | Yes | 2021-07-13 | Yes
| Registration: | When to Open? | Darnell | Yes | 2021-08-01 | No | Completed by DSIAC
|  | Email Notification? | Darnell | Yes | 2021-08-01 | No | Completed by DSIAC
| Security: | Security Plan | Darnell | Yes | 2021-07-13 | No | Darnell to discuss with Offut POC
|  | Send Classified CD | Darnell | No | 2021-10-13 | No
| Maps: | Building | Darnell | No | 2021-09-01 | No | In time to publish in read ahead
|  | Base | Darnell | Yes | 2021-09-01 | Yes | In time to publish in read ahead
|  | Local | Darnell | Yes | 2021-09-01 | Yes | In time to publish in read ahead
|  | Airport? | Darnell | Yes | 2021-09-01 | Yes | In time to publish in read ahead
|  | Social Outing? | Darnell | No | 2021-10-15 | No | In read ahead or bring copies to JPR.
| Agenda: |  |  | No | 2021-07-13 | No | Ask Dennis how to start draft…
| Presentations: | Presentation Template? | Robert | Yes | 2021-07-13 | Yes | Template and guidence e-mail complete and ready to go.
|  | Email Generated? | Darnell | No | 2021-07-13 | No
|  | Initial Notification |  | No | 2021-07-13 | No
|  | Final Reminder |  | No | 2021-07-13 | No
|  | When is due date? |  | No | 2021-10-13 | No
|  | How will they get to Offut? |  | Yes | 2021-07-13 | No
|  | Classified? |  | Yes | 2021-07-13 | No
| Roster: | When will registration close? | Darnell | Yes | 2021-10-05 | No | Coordinate with DSIAC
|  | When to expect final roster? | Darnell | Yes | 2021-10-06 | No | 1 Week Prior to JPR
| Briefing Book: | How many? |  | No | 2021-07-13 | No
|  | What to include? |  | No | 2021-07-13 | No
|  | Any other Handouts? |  | No | 2021-07-13 | No
| Survey: | Specific Questions | Darnell | No | 2021-10-08 | No
|  | How has it changed Y2Y? | Darnell | No | Post-PRM | No
| Minutes: | Generate Draft | Tyler | No | 2021-10-16 | No | Friday Prior
|  | Final Due? | Tyler | No | 2021-07-13 | No
| Proceedings: | Generate Draft | Tyler | No | 2021-10-16 | No | Friday Prior
|  | Final Due? | Tyler | No | 2021-07-13 | No
| Other: | Social Outing? | Darnell | No | 2021-07-13 | No | Darnell looking for options
|  | Hotel Room Block? | Darnell | Yes | 2021-08-01 | Yes | Prior to registration opening. See comments provided by RFL. Include AF Inns.

## AGENDA
Tuesday, 19 September 2023
| Time |  |  |  | Title | Presenter | ∑
| 7:15 | - | 8:00 | 0:45 | Registration
| 8:00 | - | 8:20 | 0:20 | Welcome & Admin | Dennis Lindell, JASPO
| 8:20 | - | 8:50 | 0:30 | Keynote: DOT&E Strategy & Implementation Plan | Dr. Jeremy Werner, DOT&E
| 8:50 | - | 9:05 | 0:15 | BREAK |  | 0:50
| #REF! | - | #REF! | 0:00 | Defeat Near-Peer Adversary Threats - RF
| 9:05 | - | 9:25 | 0:20 | RFCM Intro / FY23 OMNIBUS Projects / FY24 New Starts | Chad Zolynsky, JASPO
RFCM Techniques development
| 9:25 | - | 9:45 | 0:20 | S-20-01 / S-22-05 Modern Anti-Countermeasures Effort (MACE) | Stephen Sandy, NRL
| 9:45 | - | 10:05 | 0:20 | S-21-04 Manipulative Geo-Indicator Countermeasures (MAGIC) | Michael Burns, NRL
| 10:05 | - | 10:20 | 0:15 | BREAK |  | 1:00
| 10:20 | - | 10:40 | 0:20 | S-22-06 / S-23-06 TDOA Passive Detection System SWIL & HWIL | David Omoto, NAWCWD
| 10:40 | - | 10:50 | 0:10 | S-23-07 S-02 Passive Detection System HWIL | David Omoto, NAWCWD
Missile Warning Systems (MWS) Infrared Countermeasures (IRCM)
| 10:50 | - | 11:05 | 0:15 | S-21-03 RF-Threat Launch Detection & Tracking | Hugo Romero, NRL
| 11:05 | - | 11:20 | 0:15 | S-21-09 High-Fidelity MWS Model Development | Myles Slone, NSWC Crane
| 11:20 | - | 12:50 | 1:30 | LUNCH |  | 1:00
| #REF! |  | #REF! |  | Defeat Near-Peer Adversary Threats - IR
| 12:50 | - | 13:10 | 0:20 | IRCM Intro / FY23 OMNIBUS Projects / FY24 New Starts | Jeremy Ross, JASPO
| 13:10 | - | 13:30 | 0:20 | S-22-10 Radiometric Open Architecture Surrogate Imaging Seeker | Cole Hardman, NSWC Crane
IRCM Techniques Development
| 13:30 | - | 13:45 | 0:15 | S-22-07 Adv. Missile Feature Meas. Capability & Model Dev. | Greg Lynn, NRL
| 13:45 | - | 14:00 | 0:15 | S-21-07 Quantifying Jammer Variation | Greg Lynn, NRL
| 14:00 | - | 14:15 | 0:15 | BREAK |  | 1:10
| 14:15 | - | 14:35 | 0:20 | S-21-01 Anomaly Detection for Improved 2CIR Performance | Colin Olson, NRL
| 14:35 | - | 14:55 | 0:20 | S-22-09 RSIMS HITL Simulation of Advanced Threats | Brent Waggoner, NSWC Crane
IRCM Better analysis and understanding data
| 14:55 | - | 15:15 | 0:20 | S-23-03 FIRE Laser for IRCM | Gregory Thibault, RTI; C5ISR
| 15:15 | - | 15:30 | 0:15 | BREAK |  | 1:00
| 15:30 | - | 15:50 | 0:20 | S-23-05 MW IR Broadband Fiber | Marshall Mullins, NSWC Crane
| 15:50 | - | 16:05 | 0:15 | S-22-08 DIRCM Escort Aircraft Protection Concept | Travis Roney, NRL
| 16:05 | - | 16:20 | 0:15 | S-23-12 Threat Launch Simulator 2CIR MWS | Travis Roney / Jack Sweeney, NRL
| 16:20 | - | 16:35 | 0:15 | WRAP UP & ADJOURN |  | 0:50
Wednesday, 20 September 2023
| Time |  |  |  | Title | Presenter | ∑
| 7:15 | - | 8:00 | 0:45 | Registration
RF M&S
| 8:00 | - | 8:20 | 0:20 | RF M&S Intro / FY23 OMNIBUS Projects / FY24 New Starts | Zach Watson, JASPO
| 8:20 | - | 8:35 | 0:15 | M-16-01 JASP Model Support - Brawler | Dale Johnson
| 8:35 | - | 8:55 | 0:20 | M-16-01 JASP Model Support - SLATE & Bluemax | Jeremy Warren, BAH
| 8:55 | - | 9:15 | 0:20 | S-22-04 Red-Blue System Models for RFCM M&S | Jeremy Warren, BAH
| 9:15 | - | 9:30 | 0:15 | BREAK |  | 1:15
| 9:30 | - | 9:50 | 0:20 | S-21-06 Vertical Lift Flight Sim | Mac Dinning, CCDC/AvMC
| 9:50 | - | 10:10 | 0:20 | S-21-08 Common Terrain and Signal Server | Mac Dinning, CCDC/AvMC
| 10:10 | - | 10:30 | 0:20 | S-21-10 AFSIM HIVE Interface | Mac Dinning, CCDC/AvMC
| 10:30 | - | 10:45 | 0:15 | BREAK |  | 1:00
| 10:45 | - | 11:05 | 0:20 | V-23-06 Cyber LFT&E Full Up System Demonstration
| 11:05 | - | 11:25 | 0:20 | S-21-02 TMAP MANPADS Simulation Refactoring | Josh Davis, CCDC/AvMC
| 11:25 | - | 12:55 | 1:30 | LUNCH |  | 0:40
| 12:55 |  | 13:15 | 0:20 | S-22-01 Joint Aircraft Threat Modeling Simulation Validation | Dave Pyles, BAH
| 13:15 | - | 13:35 | 0:20 | S-22-02 Vertical Lift RFCM MS&A | Dave Pyles, BAH
| 13:35 | - | 13:55 | 0:20 | S-22-03 Simulated Engagement Analysis Lab | Lance Pearce
| 13:55 | - | 14:10 | 0:15 | BREAK |  | 1:00
|  | - | 0:00 | 0:00 | General Projects & Invited Presentations
| 14:10 | - | 14:20 | 0:10 | General Projects & Invited Presentations Intro | Dennis Lindell, JASPO
| 14:20 | - | 14:35 | 0:15 | Aircraft Survivability Education Update | Chris Adams, NPS
| 14:35 | - | 15:05 | 0:30 | G-21-01 MAESTRO Modules | Kira Lindke, ARA
| 15:05 | - | 15:25 | 0:20 | G-01-03 JCAT Intro & Future Conops | CAPT Steve Bussell
| 15:25 | - | 15:45 | 0:20 | G-01-03 JCAT INDOPACOM Exercise Outbrief | CDR Joey Walker
| 15:45 | - | 15:55 | 0:10 | WRAP UP & ADJOURN |  | 1:35
| 15:55 | - | 17:25 | 1:30 | PMSG Closed Session
Thursday, 21 September 2023
| Time |  |  |  | Title | Presenter | ∑
| 7:15 | - | 8:00 | 0:45 | Registration
| 8:10 | - | 8:10 | 0:00 | Improve Aircraft Force Protection
| 8:00 | - | 8:10 | 0:10 | Defeat Fire Intro | Dennis Lindell, JASPO
| 8:10 | - | 8:30 | 0:20 | V-19-02 Efficient, Crash-Tolerant Fuel Bladder | Allison Monclova, NAWCWD
| 8:30 | - | 8:50 | 0:20 | V-20-01 NGFM Validation | Carlos Suarez, 704TG-OL/AC
| 8:50 | - | 9:20 | 0:30 | V-23-02 NGFM v2.0 Development & V-23-05 NGFM Data | Carlos Suarez, 704TG-OL/AC
| 9:20 | - | 9:35 | 0:15 | BREAK |  | 1:20
| 9:35 | - | 9:55 | 0:20 | V-23-01 PAO Qualification | Carlos Suarez, 704TG-OL/AC
| 9:55 | - | 10:05 | 0:10 | Vulnerability Accuracy & Confidence Intro | Dennis Lindell, JASPO
| 10:05 | - | 10:25 | 0:20 | V-23-03 Survivability Digital Ecosystem | Scott Wacker, 704TG-OL/AC
| 10:25 | - | 10:45 | 0:20 | Invited: Assessing Aircraft Survivability Against DEW Survey Results | Rodney Stewart, SURVICE
| 10:45 | - | 11:00 | 0:15 | BREAK |  | 1:10
| 11:00 | - | 11:20 | 0:20 | M-16-01 JASP Model Support - COVART | Jon Smith, EZJA
| 11:20 | - | 11:40 | 0:20 | V-23-04 AJEM Converters | Russell Dibelka, DAC
| 11:40 | - | 12:00 | 0:20 | V-21-01 HE Threat Sensitivity Studies | Tim Staley, EZJA
| 12:00 | - | 12:20 | 0:20 | V-21-03 Pedigree Configuration Management | Jon Marshall, EZJA
| 12:20 | - | 12:30 | 0:10 | WRAP UP & ADJOURN |  | 1:20
JPR FY22 Projects not considered for FY23
[5 empty] | S-20-04 Scoring Optical Break Lock (OBL) for Open Loop CM Tests | Rick Moore, NRL
Additional Projects subject to Intro Brief
S-23-01 Intelligent CM Control
S-23-02 REVAMP
S-23-09 Synergistic Expendables and Jammers for Assault Helicopters
S-23-10 Imaging Surrogate Tracker w/AI for Expendable CCM
S-23-11 Advanced Missile Feature Detection and Tracking Evaluation System
S-23-12 Threat Launch Simulator for 2-Color MWS
S-23-13 Integration of IC Threat Jamming & EP Simulations
S-23-14 Combat Virtual Reality (CVR)

## BRIEFING TRACKER
Briefing Day | Title (update in agenda tab) | Presenter (update in agenda tab) | Responsible JASPO DPM | Presentation Notice & Guidance Sent Y/N | Confirmed (date, time, briefer, title) Y/N | Date Draft Received (Due 8/21) | Date JASP Comments Provided | Date Final Received (Due 9/08) | Class | Distro | Downgrading and/or controlling block | Permission to Publish (CUI, DISTRO D) | Permission to Publish (S//NF, DISTRO D)
Tuesday | Welcome & Admin | Dennis Lindell, JASPO | Dennis Lindell | N/A | Yes | 2023-08-21 |  | 2023-09-08
| Keynote: DOT&E Strategy & Implementation Plan | Dr. Jeremy Werner, DOT&E | Dennis Lindell | N/A | Yes
| RFCM Introduction / FY23 OMNIBUS SAR Projects / FY24 New Starts | Chad Zolynsky, JASPO | Chad Zolynsky | Yes | Yes |  |  |  | CUI | D
| S-20-01 / S-22-05 Modern Anti-Countermeasures Effort (MACE) | Stephen Sandy, NRL | Chad Zolynsky | Yes | Yes | 2023-08-11 | 2023-08-24 | 2023-09-07 | S//REL | D
| S-21-04 Manipulative Geo-Indicator Countermeasures (MAGIC) | Michael Burns, NRL | Chad Zolynsky | Yes | Yes | 2023-08-11 | 2023-08-24 | 2023-09-07 | S//NF | D
| S-22-06 / S-23-06 TDOA Passive Detection System SWIL & HWIL | David Omoto, NAWCWD | Chad Zolynsky | Yes | Yes | 2023-08-22 | 2023-08-24 | 2023-09-08 | S//NF | D
| S-23-07 S-02 Passive Detection System HWIL | David Omoto, NAWCWD | Chad Zolynsky | Yes | Yes | 2023-08-22 | 2023-08-24 | 2023-09-08 | S//NF | D
| S-21-03 RF-Threat Launch Detection & Tracking | Hugo Romero, NRL | Chad Zolynsky | Yes | Yes | 2023-08-21 | 2023-08-24 | 2023-09-07 | S | D
| S-21-09 High-Fidelity MWS Model Development | Myles Slone, NSWC Crane | Chad Zolynsky | Yes | Yes | 2023-08-24 | 2023-08-24 |  | S | D
| IRCM Introduction / FY23 OMNIBUS SAR Projects / FY24 New Starts | Jeremy Ross, JASPO | Jeremy Ross | Yes | Yes |  |  |  | CUI | D
| S-22-10 Radiometric Open Architecture Surrogate Imaging Seeker (R-OASIS) | Cole Hardman, NSWC Crane | Jeremy Ross | Yes | Yes (Brent or Myles) | 2023-09-07 |  |  | CUI | D
| S-22-07 Adv. Missile Feature Meas. Capability & Model Dev. | Greg Lynn, NRL | Jeremy Ross | Yes | Yes | 2023-09-08 |  |  | S//NF | D
| S-21-07 Quantifying Jammer Variation | Greg Lynn, NRL | Jeremy Ross | Yes | Yes | 2023-09-08 |  |  | S | D
| S-21-01 Anomaly Detection for Improved 2CIR Performance | Colin Olson, NRL | Jeremy Ross | Yes | Yes | 2023-09-07 |  |  | CUI | D
| S-22-09 RSIMS HITL Simulation of Advanced Threats | Brent Waggoner, NSWC Crane | Jeremy Ross | Yes | Yes | 2023-08-18 |  | 2023-09-06 | CUI | D
| S-23-03 FIRE Laser for IRCM | Gregory Thibault, RTI; C5ISR | Jeremy Ross | Yes | Yes | 2023-08-22 |  |  | CUI | D
| S-22-08 DIRCM Escort Aircraft Protection Concept | Travis Roney, NRL | Jeremy Ross | Yes | Yes | 2023-08-21 | 2023-08-24 | 2023-09-07 | S | D
| S-23-05 MW IR Broadband Fiber | Marshall Mullins, NSWC Crane | Jeremy Ross | Yes | Yes (Backup briefer Brent Waggoner/Myles Slone briefing Class NICEL) | 2023-08-10 |  |  | S//NF | E
| S-23-12 Threat Launch Simulator for 2-Color MWS | Travis Roney / Jack Sweeney, NRL | Chad Zolynsky | Yes | Yes | 2023-08-23 |  |  | CUI | D
Wednesday | RF M&S Introduction / FY23 OMNIBUS M&S Projects / FY24 New Starts | Zach Watson, JASPO | Zachary Watson
| M-16-01 JASP Model Support - Brawler | Dale Johnson | Zachary Watson
| M-16-01 JASP Model Support - SLATE & Bluemax | Hugh Griffis, AFLCMC/EZJ | Zachary Watson
| S-22-04 Red-Blue System Models for RFCM M&S | Hugh Griffis, AFLCMC/EZJ | Zachary Watson
| SLATE and ESAMS 5.7 Update | Hugh Griffis, AFLCMC/EZJ | Zachary Watson
| S-21-06 Vertical Lift Flight Sim | Mac Dinning, CCDC/AvMC | Zachary Watson
| S-21-08 Common Terrain and Signal Server | Mac Dinning, CCDC/AvMC | Zachary Watson
| S-21-10 AFSIM HIVE Interface | Mac Dinning, CCDC/AvMC | Zachary Watson
| S-21-02 TMAP MANPADS Simulation Refactoring | Josh Davis, CCDC/AvMC | Zachary Watson
Zachary Watson
| S-22-02 Vertical Lift RFCM MS&A | Dave Pyles, BAH | Zachary Watson
| General Projects & Invited Presentations Intro | Dennis Lindell, JASPO | Dennis Lindell | N/A | Yes
| Aircraft Survivability Education Update | Chris Adams, NPS | Dennis Lindell | 2023-07-29 | Yes | 2023-08-22 | 2023-08-25 | 2023-09-05 | CUI | C
| G-21-01 MAESTRO Modules | Kira Lindke, ARA | Dennis Lindell | 2023-07-29 | Yes | 2023-08-22 | 2023-08-25 | 2023-09-08 | CUI | D
| V-23-06 Cyber LFT&E Full Up System Demonstration |  | Dennis Lindell | 2023-07-29 |  | 2023-08-29 | 2023-08-30 |  | CUI | D
| G-01-03 JCAT Intro & Future Conops | CAPT Steve Bussell | Stephen Bussell |  | Yes | 2023-08-22
| G-01-03 JCAT INDOPACOM Exercise Outbrief | CDR Joey Walker | Stephen Bussell |  | Yes
Thursday | Defeat Fire Intro | Dennis Lindell, JASPO | Carrell McAllister | N/A | Yes
| V-19-02 Efficient, Crash-Tolerant Fuel Bladder | Allison Monclova, NAWCWD | Carrell McAllister | Yes | Yes | 2023-08-21 | 2023-08-23 | 2023-09-08 | CUI | D
| V-20-01 NGFM Validation | Carlos Suarez, 704TG-OL/AC | Carrell McAllister | Yes | Yes | 2023-08-21 | 2023-08-23 | 2023-09-08 | CUI | C
| V-23-02 NGFM v2.0 Development & V-23-05 NGFM Data | Carlos Suarez, 704TG-OL/AC | Carrell McAllister | Yes | Yes | 2023-08-21 | 2023-08-24 | 2023-09-08 | CUI | C
| V-23-01 PAO Qualification | Carlos Suarez, 704TG-OL/AC | Carrell McAllister | Yes | Yes | 2023-08-21 | 2023-08-23 | 2023-09-08 | CUI | D
| Vulnerability Accuracy & Confidence Intro | Dennis Lindell, JASPO | Carrell McAllister | N/A | Yes
| V-23-03 Survivability Digital Ecosystem | Scott Wacker, 704TG-OL/AC | Carrell McAllister | Yes | Yes | 2023-08-18 | 2023-08-18 |  | CUI | C
| M-16-01 JASP Model Support - COVART | Jon Smith, EZJA | Carrell McAllister | Yes | Yes | 2023-08-18 | 2023-08-18 | 2023-08-28 | CUI | C
| V-23-04 AJEM Converters | Russell Dibelka, DAC | Carrell McAllister | Yes | Yes | 2023-08-28 | 2023-08-30 | 2023-09-08 | CUI | D
| V-21-01 HE Threat Sensitivity Studies | Tim Staley, EZJA | Carrell McAllister | Yes | Yes | 2023-08-16 | 2023-08-17 | 2023-08-17 | CUI | D
| V-21-03 Pedigree Configuration Management | Jon Marshall, EZJA | Carrell McAllister | Yes | Yes | 2023-08-18 | 2023-08-25 | 2023-09-08 | S//NF | D
[9 empty] | U | A
[9 empty] | CUI | B
[9 empty] | C | C
[9 empty] | S | D
[9 empty] | S//NF | E
[9 empty] | S//REL | F
Carrell McAllister
Chad Zolynsky
Darnell Marbury
Dennis Lindell
Jeremy Ross
Stephen Bussell
Zachary Watson

## MONDAY (hidden)
Monday, 18 Oct 2021 | [5 empty] | Day 1 (Monday) Roster
Time |  |  |  | Title | Presenter | Name | Last/First Name | First Name | Last Name | Organization | Address | Phone | Email | CAC | US Citizen
0:00 | - | 1:00 | 1:00 | Registration |  | Mr. Dale Atkinson | Atkinson, Dale | Dale | Atkinson | JASPO | 113 Ivy Creek Ln. , Mooresville, North Carolina 28115-0000 | (704) 230-1366 | daleatk@gmail.com | Yes | Yes
1:00 | - | 1:10 | 0:10 | Welcome | Dennis Lindell, JASPO | Mr. Angelo Bianchini | Bianchini, Angelo | Angelo | Bianchini | NAWCWD | 575 I Ave NAWCWD, Point Mugu, California 93042 | (979) 575-1387 | angelo.bianchini@navy.mil | Yes | Yes
1:10 |  | 1:10 | 0:00 | JASP Cyber Survivability Working Group | Tentative, Invite Only | Mr. Michael Breslin | Breslin, Michael | Michael | Breslin | Independent Contractor | 5120 SW 117th Way , Cooper City, Florida 33330 | (614) 325-9540 | breslin.mc@gmail.com | No | No
1:10 | - | 2:30 | 1:20 | TBD |  | Mr. Stephan Bussell | Bussell, Stephan | Stephan | Bussell | NAVAIR | 5833 Cranswick Ct , Haymarket, Virginia 20169 | (703) 695-2162 | stephan.bussell@navy.mil | Yes | No
2:30 | - | 2:45 | 0:15 | BREAK |  | Mr Mark Chamberlin Jr | Chamberlin, Mark | Mark | Chamberlin | ASDAT | 304 Squirrel Hollow Dr , Enterprise, Alabama 36330 | (907) 978-3532 | mark.s.chamberlin2.mil@mail.mil | Yes | Yes
2:45 | - | 4:05 | 1:20 | TBD |  | Mr. Daniel Cifredo | Cifredo, Daniel | Daniel | Cifredo | PMA 272 | 6201 Cargo Hold Ave , Jacksonville, Florida 32221 | (904) 317-1970 | daniel.cifredo@navy.mil | Yes | Yes
4:05 | - | 4:10 | 0:05 | WRAP UP & ADJOURN |  | Dr. Mark Couch | Couch, Mark | Mark | Couch | Institute for Defense Analyses | 4850 Mark Center Dr. , Alexandria, Virginia 22311-1882 | (703) 845-2530 | mcouch@ida.org | Yes | Yes
[6 empty] | Mr. James Davis | Davis, James | James | Davis | AFLCMC/EZJA | 1970 Monahan Way, Bldg 11A , WPAFB, Ohio 45433-7210 | (937) 904-4114 | james.davis.123@us.af.mil | Yes | No
UNCLASSIFIED | [5 empty] | Mr. Peter Emig | Emig, Peter | Peter | Emig | ACE Consulting Group | 22299 Exploration Dr. Suite 400 ACE Consulting Group, Lexington Park, Maryland 20653 | (240) 237-8031 | peter.emig@acegroupllc.com | Yes | Yes
CLASSIFIED | [5 empty] | Mr. Ron Godlewski | Godlewski, Ron | Ron | Godlewski | Selex Galileo Inc | 13125 Paseo Barranco , Monterey, California 93908 | (000) 000-0000 | ronald.godlewski@selexgalileoinc.com | No | Yes
[6 empty] | Mr. Bruce Graves | Graves, Bruce | Bruce | Graves | US Army PEO Aviation | 5302 Burose Road , Redstone Arsenal, Alabama 35898 | (256) 842-5451 | bruce.r.graves2.civ@mail.mil | Yes | Yes
[6 empty] | Mr. Hugh Griffis | Griffis, Hugh | Hugh | Griffis | AFLCMC/EZJ | 1970 Monahan Way Building 11A , Wright Patterson Air Force Base, Ohio 45433-7207 | (937) 904-4405 | hugh.griffis@us.af.mil | Yes | Yes
[6 empty] | Lt. Tyler Harrell | Harrell, Tyler | Tyler | Harrell | NAVAIR | 701 S. Courthouse Rd Naval Support Facility - Arlington, Arlington, Virginia 22204-2589 | (517) 927-7842 | tyler.j.harrell@navy.mil | Yes | Yes
[6 empty] | Rich Huffman | Huffman, Rich | Rich | Huffman | Air Force Institute of Technology | 2950 Hobson Way , Wright-Patterson AFB, Ohio 45433-7765 | (575) 678-1251 | richard.huffman@us.af.mil | Yes | Yes
[6 empty] | Mr. Erik Johnson | Johnson, Erik | Erik | Johnson | TenCate Advanced Armor Design | 1051 O'Neil Dr. , Hebron, Ohio 43025 | (740) 527-0176 | ejohnson@tcaad-us.com | No | Yes
[6 empty] | Mr. Gregory Johnson | Johnson, Gregory | Gregory | Johnson | SFAE-IEW-SE | 6726 Odyssey Drive , Huntsville, Alabama 35806-3302 | (256) 955-7173 | gregory.johnson6.civ@mail.mil | Yes | No
[6 empty] | Mr. Dennis Lindell | Lindell, Dennis | Dennis | Lindell | Joint Aircraft Survivability Program Office | 701 S. Courthouse Rd Building 15, Suite 1G140 , Arlington, Virginia 22204-2489 | (703) 604-2622 | dennis.lindell@navy.mil | Yes | Yes
[6 empty] | Andrew Lovejoy | Lovejoy, Andrew | Andrew | Lovejoy | 2-211th AVN BN | 7602 S. Airport Rd HHC 2-211th AVN BN, West Jordan, Utah 84084 | (801) 816-3410 | andrew.g.lovejoy2.mil@mail.mil | Yes | Yes
[6 empty] | Mr. Darnell Marbury | Marbury, Darnell | Darnell | Marbury | Joint Aircraft Survivability Program Office | 701 S. Courthouse Rd. Building 15, Suite 1G140 , Arlington, Virginia 22204-2489 | (703) 604-0387 | darnell.marbury@navy.mil | Yes | Yes
[6 empty] | Jonathan Marshall | Marshall, Jonathan | Jonathan | Marshall | AFLCMC/EZJA | 1970 Monahan Way Area B, Bldg 11A , Wright-Patterson Air Force Base, Ohio 45433 | (937) 904-7057 | jonathan.marshall.9@us.af.mil | Yes | Yes
[6 empty] | Carrell McAllister | McAllister, Carrell | Carrell | McAllister | JASPO | 701 S Courthouse Rd Bldg 15, Suite 1G140 , Arlington, Virginia 22204 | (703) 604-7118 | carrell.mcallister@navy.mil | Yes | Yes
[6 empty] | Mr. Ken McCormick | McCormick, Ken | Ken | McCormick | TETRA | 4545 Fowler Rd. Attn: MSIC7 , Redstone Arsenal, Alabama 35898-5500 | (256) 313-7700 | ken.mccormick@msic.dia.mil | Yes | Yes
[6 empty] | Mr. Ott Oudom | Oudom, Ott | Ott | Oudom | NAVAIR 4.5.19.4 | 6201 Aviation Ave NAVAIR, Jacksonville, Florida 32222 | (904) 317-1996 | Ott.Oudom@navy.mil | Yes | Yes
[6 empty] | Mr. Christopher Phlegar | Phlegar, Christopher | Christopher | Phlegar | Northrop Grumman | 301 Voyager Way NW Northrop Grumman, Huntsville, Alabama 35806 | (224) 200-7778 | christopher.phlegar@ngc.com | No | Yes
[6 empty] | Mr. Jeffrey Poole | Poole, Jeffrey | Jeffrey | Poole | PEO AVN | Bldg 4500 Martin RD RTC, Redstone Arsenal, Alabama 35898 | (256) 503-5997 | jeffrey.w.poole.civ@mail.mil | Yes | Yes
[6 empty] | Dr. Marc Portanova | Portanova, Marc | Marc | Portanova | Applied Aviation Technology Directorate | 409 Lee Blvd , Fort Eustis, Virginia 23604-5577 | (757) 878-4238 | marc.a.portanova.civ@mail.mil | Yes | Yes
[6 empty] | Mr. David Rios | Rios, David | David | Rios | USCENTCOM (Cloud Lake) | PO Box 71 , San Antonio, Florida 33576 | (813) 529-8102 | david.h.rios.ctr@mail.mil | Yes | Yes
[6 empty] | Mr. Jeffrey Rothstein | Rothstein, Jeffrey | Jeffrey | Rothstein | I/SMO | 5285 Shawnee Road MTSI, Alexandria, Virginia 22312 | (202) 404-6898 | jeffrey.a.rothstein.ctr@mail.mil | Yes | Yes
[6 empty] | Dr. Gregory Ruderman | Ruderman, Gregory | Gregory | Ruderman | DOT&E/Live Fire | 1700 Defense Pentagon 1D548 , Washington, District of Columbia 20301 | (703) 692-1706 | gregory.a.ruderman.civ@mail.mil | Yes | Yes
[6 empty] | Mr. Michael Schuck | Schuck, Michael | Michael | Schuck | SURVICE Engineering Company | 4141 Colonel Glenn Hwy. Suite 209 , Dayton, Ohio 45431 | (937) 431-9914 | michael.schuck@survice.com | Yes | Yes
[6 empty] | Mr. Nathan Smith | Smith, Nathan | Nathan | Smith | Georgia Tech Research Institute | 925 Dalney St , Atlanta, Georgia 30332 | (404) 407-7340 | nathan.smith@gtri.gatech.edu | Yes | Yes
[6 empty] | Mr. Stephen Thompson | Thompson, Stephen | Stephen | Thompson | Georgia Tech Research Institute | 400 Tenth Street CRB 419 , Atlanta, Georgia 30332 | (404) 831-7967 | steve.thompson@gtri.gatech.edu | Yes | Yes
[6 empty] | Mr. Warren Whitmire | Whitmire, Warren | Warren | Whitmire | ASDAT | Building 5000 Lucky Star Street , Fort Rucker, Alabama 36362 | (334) 255-2441 | warren.j.whitmire.civ@mail.mil | Yes | No
Darnell updates when
registration begins